## Akhil
Agile Task Board
Assigned To: | C Akhil Chowdary
Use Case: | Online Orders And Cancellations
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Order
Create SQL Server table named "OrdersTable" | 0.5 | 1
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create OrdersService using Angular for CRUD operations | 2 | 3
UI - Create Angular Component & Template for "Orders Page" using Bootstrap & Angular | 2 | 2 | issues with routing, and service
UI - Create Angular Component & Template for "Create Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1.5
Create OrderDetails
Create SQL Server table named "OrderDetailsTable" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create OrdersService using Angular for CRUD operations | 1 | 1
UI - Create Angular Component & Template for "OrderDetails Page" using Bootstrap & Angular | 2 | 2 | character casing issues
UI - Create Angular Component & Template for "Create OrderDetails Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit OrderDetails Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete OrderDetails Page" using Bootstrap & Angular | 1 | 2

## Abhishek
Agile Task Board
Assigned To: | Abhishek Pratap Singh
Use Case: | Upload Offline Order And Offline Return
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours
UploadOfflineOrders
Create SQL Server table named "Offline Order " | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5 | issues with routing, and service
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create OfflineOrder service using Angular for CRUD operations | 2 | 3
UI - Create Angular Component & Template for "Uploading Orders Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit OfflineOrder Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete OfflineOrder Page" using Bootstrap & Angular | 1 | 2
UploadOfflineOrderDetails
Create SQL Server table named "OfflineOrder Details " | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create offline order service using Angular for CRUD operations | 1 | 1 | issues with routing, and service
UI - Create Angular Component & Template for "Updating offline Orders Detail Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete OfflineOrderDetail Page" using Bootstrap & Angular | 1 | 1
ReturnOfflineOrder
Create SQL Server table named "Offline Return" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1

## Sravani
Agile Task Board
Assigned To: | Chennareddy Sravani
Use Case: | Admin Report And SalesReport
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours
Admin And SalesReport
Create SQL Server table named "Admin " | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations, "View Sales Report" | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create OrdersService using Angular for CRUD operations | 2 | 2 | issues with routing, and service
UI - Create Angular Component & Template for "Login Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Retailer Registration Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Home Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " View Sales Reports Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for " Edit Profile Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Add Sales Person Page" using Bootstrap & Angular | 2 | 3

## Prafull
Agile Task Board
Assigned To: | Prafull Sharma
Use Case: | Retailers Report And Address
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours
Retailer And Address
Create SQL Server table named "Retailers ", "Address ","Retailer Report" | 1 | 1
Create Stored Procedures for all CRUD Operations | 3 | 3
Prepare Test Cases using Excel for all CRUD operations | 2 | 3
Prepare Test Cases using MSUnit test cases for all CRUD operations | 3 | 4
UI - Create OrdersService using Angular for CRUD operations | 2 | 3 | issues with routing, and service
UI - Create Angular Component & Template for "Retailer Page & Address management Page " using Bootstrap & Angular | 4 | 4
UI - Create Angular Component & Template for "Add Retailer and Add Address " using Bootstrap & Angular | 4 | 4
UI - Create Angular Component & Template for "Update Retailer and Update Address Page" using Bootstrap & Angular | 4 | 5
UI - Create Angular Component & Template for "Delete Retailer and Delete Address" using Bootstrap & Angular | 2 | 3

## Ayush
Agile Task Board
Assigned To: | Ayush Agrawal
Use Case | View SalesPerson Details and Online Return
Team: | Team B
Use Case | Actual No. of Hours Expected | Actual No. of Hours
SalesPerson And Online Returns
Create SQL Server table named "SalesPerson" and OnlineReturn | 1 | 1
Create Stored Procedures for all CRUD Operations for SalesPerson and OnlineReturn | 3 | 4
Prepare Test Cases using Excel for all CRUD operations for SalesPerson and OnlineReturn | 2 | 2.5
Prepare Test Cases using MSUnit for all CRUD operations for SalesPerson and OnlineReturn | 3 | 4
UI - Create Service using Angular for CRUD operations | 2 | 3
UI - "Create SalesPerson Page" using Angular | 2 | 3
UI - Create page for "OnlineReturn Page" | 3 | 4
UI - Create "Create SalesPerson Page" and "Create OnlineReturn Page" | 4 | 5 | issues with, objects and character casing
UI - Create for "Edit SalesPerson Page" and "Edit OnlineReturn Page" | 4 | 5.5
UI - Create "Delete SalesPerson Page" and "Delete OnlineReturn | 2 | 3

## Arshpreet
Agile Task Board
Assigned To: | Arshpreet
Use Case: | Products
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours
Products
Create SQL Server table named "Products" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create OrdersService using Angular for CRUD operations | 2 | 2
UI - Create Angular Component & Template for Products Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Product Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Product Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Product Page" using Bootstrap & Angular | 1 | 1